## Dashboard
PRT563 Danala Group 17 – Project Task Tracker
Timeline: 1 Aug 2026 → 16 Oct 2026 ¦ A1 due 07 Aug ¦ A2 due 11 Sep ¦ A3 Mid-semester Test ¦ A4 due 16 Oct ¦ Group Leader: Nitesh Raj Chaudhary
ASSESSMENT TIMELINE
Assessment | Weight | Start | Due Date | Status | Tasks | Done | % Complete
Assessment 1 – Group Project Plan | 10% | 2026-08-01 | 2026-08-07 | Done | 7 | 7 | 100%
Assessment 2 – Group Project Presentation | 30% | 2026-08-08 | 2026-09-11 | Done | 9 | 9 | 100%
Assessment 3 – Individual Mid-Semester Test | 20% | 2026-09-12 | 2026-09-26 | Done | 8 | 8 | 100%
Assessment 4 – Group Project Report | 40% | 2026-09-27 | 2026-10-16 | In Progress | 19 | 18 | 95%
PROJECT SNAPSHOT
Metric | Value
Total Tasks | 43
Done | 42
In Progress | 1
To Do | 0
Total Story Points | 124
Story Points Done | 122
% Tasks Complete | 98%
% Points Complete | 98%
WORKLOAD BY MEMBER
Member | Assigned | Done | In Progress | Story Points | Points Done | % Complete
Nitesh Raj Chaudhary | 16 | 15 | 1 | 45 | 43 | 94%
Dilliram Dhakal | 8 | 8 | 0 | 22 | 22 | 100%
Roshan Kumar Shrestha | 9 | 9 | 0 | 30 | 30 | 100%
Dipesh Sedhai | 10 | 10 | 0 | 27 | 27 | 100%
OPEN / CRITICAL TASKS (current)
Key | Summary | Assignee | Status | Priority | Due Date
PRT-43 | Final QC and submit Assessment 4 | Nitesh | In Progress | Critical | 2026-10-16

## All Tasks
Key | Summary | Assessment | Type | Assignee | Reporter | Status | Priority | Story Points | Sprint | Start Date | Due Date | Labels | Description
PRT-1 | Kick-off meeting & role allocation | Assessment 1 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 1 | Sprint 1 (A1) | 2026-08-01 | 2026-08-02 | planning | Agree roles, tools, communication channel
PRT-2 | Draft project scope and objectives | Assessment 1 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 1 (A1) | 2026-08-01 | 2026-08-03 | planning | Darwin supermarket DB goals
PRT-3 | Research NT retail supply-chain constraints | Assessment 1 | Research | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 1 (A1) | 2026-08-01 | 2026-08-04 | research | Stuart Hwy, wet season, no local DC
PRT-4 | Stakeholder analysis | Assessment 1 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 1 (A1) | 2026-08-02 | 2026-08-04 | planning | Key stakeholders for multi-store retail
PRT-5 | Risk register and timeline | Assessment 1 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 1 (A1) | 2026-08-02 | 2026-08-05 | planning | Risks + high-level schedule
PRT-6 | Compile Group Project Plan document | Assessment 1 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 4 | Sprint 1 (A1) | 2026-08-03 | 2026-08-06 | documentation | Full plan document
PRT-7 | Peer review & final QC – Assessment 1 | Assessment 1 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 2 | Sprint 1 (A1) | 2026-08-05 | 2026-08-07 | submission | Due 07/08/2026 16:59
PRT-8 | Design EER model (Chen notation) | Assessment 2 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 5 | Sprint 2 (A2) | 2026-08-08 | 2026-08-18 | modelling | Enhanced ER diagram
PRT-9 | Draw UML class diagram | Assessment 2 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 2 (A2) | 2026-08-10 | 2026-08-20 | modelling | UML from EER
PRT-10 | Normalise schema to 3NF | Assessment 2 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | High | 4 | Sprint 2 (A2) | 2026-08-12 | 2026-08-22 | modelling | Relational schema 3NF
PRT-11 | Implement SQLite DB + sample data | Assessment 2 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | Critical | 5 | Sprint 2 (A2) | 2026-08-18 | 2026-08-28 | implementation | Tables + seed data
PRT-12 | Write 4 SQL use cases | Assessment 2 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 4 | Sprint 2 (A2) | 2026-08-20 | 2026-08-30 | queries | Increasing complexity
PRT-13 | Author Assessment 2 report sections | Assessment 2 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 5 | Sprint 2 (A2) | 2026-08-25 | 2026-09-05 | documentation | Modelling + implementation write-up
PRT-14 | Create Assessment 2 presentation slides | Assessment 2 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | High | 4 | Sprint 2 (A2) | 2026-08-28 | 2026-09-08 | presentation | PPT for group presentation
PRT-15 | Rehearse presentation | Assessment 2 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 2 | Sprint 2 (A2) | 2026-09-08 | 2026-09-10 | presentation | Group dry-run
PRT-16 | Submit Assessment 2 | Assessment 2 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 1 | Sprint 2 (A2) | 2026-09-10 | 2026-09-11 | submission | Due 11/09/2026 16:59
PRT-17 | Revise EER / normalisation / SQL topics | Assessment 3 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 3 (A3) | 2026-09-12 | 2026-09-20 | study | Individual test prep
PRT-18 | Revise EER / normalisation / SQL topics | Assessment 3 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 3 (A3) | 2026-09-12 | 2026-09-20 | study | Individual test prep
PRT-19 | Revise EER / normalisation / SQL topics | Assessment 3 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 3 (A3) | 2026-09-12 | 2026-09-20 | study | Individual test prep
PRT-20 | Revise EER / normalisation / SQL topics | Assessment 3 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 3 (A3) | 2026-09-12 | 2026-09-20 | study | Individual test prep
PRT-21 | Sit Individual Middle Semester Test | Assessment 3 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 2 | Sprint 3 (A3) | 2026-09-22 | 2026-09-26 | exam | Individual assessment (20%)
PRT-22 | Sit Individual Middle Semester Test | Assessment 3 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | Critical | 2 | Sprint 3 (A3) | 2026-09-22 | 2026-09-26 | exam | Individual assessment (20%)
PRT-23 | Sit Individual Middle Semester Test | Assessment 3 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | Critical | 2 | Sprint 3 (A3) | 2026-09-22 | 2026-09-26 | exam | Individual assessment (20%)
PRT-24 | Sit Individual Middle Semester Test | Assessment 3 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | Critical | 2 | Sprint 3 (A3) | 2026-09-22 | 2026-09-26 | exam | Individual assessment (20%)
PRT-25 | Translate EER → Neo4j property graph model | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 5 | Sprint 4 (A4) | 2026-09-27 | 2026-10-02 | modelling,neo4j | Labels, relationships, optimisations
PRT-26 | Create Bloom / graph model visualisation | Assessment 4 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 4 (A4) | 2026-09-28 | 2026-10-03 | modelling,visualisation | Figure 1
PRT-27 | Write Cypher import scripts (constraints + data) | Assessment 4 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | Critical | 5 | Sprint 4 (A4) | 2026-09-29 | 2026-10-05 | implementation,cypher | import.txt pure Cypher
PRT-28 | Prepare CSV sample data files | Assessment 4 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 4 (A4) | 2026-09-29 | 2026-10-04 | data | All entity CSVs
PRT-29 | Write 4 Cypher query use cases | Assessment 4 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | High | 4 | Sprint 4 (A4) | 2026-10-03 | 2026-10-08 | queries,cypher | queries.txt
PRT-30 | Run & screenshot Cypher use cases | Assessment 4 | Task | Roshan Kumar Shrestha | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 4 (A4) | 2026-10-08 | 2026-10-10 | evidence | Figures 2–5
PRT-31 | PageRank centrality (GDS) | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 3 | Sprint 4 (A4) | 2026-10-05 | 2026-10-10 | algorithms,gds | Weighted PageRank
PRT-32 | Degree Centrality (GDS) | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 2 | Sprint 4 (A4) | 2026-10-06 | 2026-10-11 | algorithms,gds | Weighted Degree
PRT-33 | Betweenness Centrality (GDS) | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 2 | Sprint 4 (A4) | 2026-10-07 | 2026-10-12 | algorithms,gds | Betweenness
PRT-34 | Jaccard Node Similarity (GDS) | Assessment 4 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | Critical | 3 | Sprint 4 (A4) | 2026-10-06 | 2026-10-11 | algorithms,gds | Jaccard metric
PRT-35 | Cosine Node Similarity (GDS) | Assessment 4 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 2 | Sprint 4 (A4) | 2026-10-07 | 2026-10-12 | algorithms,gds | Cosine metric
PRT-36 | Screenshot all GDS results | Assessment 4 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 4 (A4) | 2026-10-11 | 2026-10-13 | evidence | Figures 6–9
PRT-37 | Write Centrality section of report | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 4 (A4) | 2026-10-10 | 2026-10-13 | documentation | Comparison + recommendations
PRT-38 | Write Similarity section of report | Assessment 4 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 4 (A4) | 2026-10-10 | 2026-10-13 | documentation | Jaccard vs Cosine
PRT-39 | Write Modelling + Implementation sections | Assessment 4 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | High | 3 | Sprint 4 (A4) | 2026-10-08 | 2026-10-12 | documentation | Design decisions
PRT-40 | Write Discussions, Limitations, Conclusion | Assessment 4 | Task | Dilliram Dhakal | Nitesh Raj Chaudhary | Done | Medium | 2 | Sprint 4 (A4) | 2026-10-11 | 2026-10-14 | documentation | Limitations + future work
PRT-41 | Integrate final report + embed figures | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | Done | Critical | 4 | Sprint 4 (A4) | 2026-10-13 | 2026-10-15 | documentation | Final DOCX with Bloom + screenshots
PRT-42 | Package repository (scripts + CSVs) | Assessment 4 | Task | Dipesh Sedhai | Nitesh Raj Chaudhary | Done | High | 2 | Sprint 4 (A4) | 2026-10-14 | 2026-10-15 | submission | GitHub / OneDrive URL
PRT-43 | Final QC and submit Assessment 4 | Assessment 4 | Task | Nitesh Raj Chaudhary | Nitesh Raj Chaudhary | In Progress | Critical | 2 | Sprint 4 (A4) | 2026-10-15 | 2026-10-16 | submission | Due 16/10/2026 16:59

## Nitesh's Board
Nitesh Raj Chaudhary – Personal Task Board
Tasks: 16 ¦ Done: 15 ¦ Story Points: 43/45 ¦ Completion: 94%
Key | Summary | Assessment | Status | Priority | Story Points | Due Date | Labels
PRT-1 | Kick-off meeting & role allocation | Assessment 1 | Done | Critical | 1 | 2026-08-02 | planning
PRT-2 | Draft project scope and objectives | Assessment 1 | Done | High | 3 | 2026-08-03 | planning
PRT-7 | Peer review & final QC – Assessment 1 | Assessment 1 | Done | Critical | 2 | 2026-08-07 | submission
PRT-8 | Design EER model (Chen notation) | Assessment 2 | Done | Critical | 5 | 2026-08-18 | modelling
PRT-13 | Author Assessment 2 report sections | Assessment 2 | Done | Critical | 5 | 2026-09-05 | documentation
PRT-15 | Rehearse presentation | Assessment 2 | Done | High | 2 | 2026-09-10 | presentation
PRT-16 | Submit Assessment 2 | Assessment 2 | Done | Critical | 1 | 2026-09-11 | submission
PRT-17 | Revise EER / normalisation / SQL topics | Assessment 3 | Done | High | 3 | 2026-09-20 | study
PRT-21 | Sit Individual Middle Semester Test | Assessment 3 | Done | Critical | 2 | 2026-09-26 | exam
PRT-25 | Translate EER → Neo4j property graph model | Assessment 4 | Done | Critical | 5 | 2026-10-02 | modelling,neo4j
PRT-31 | PageRank centrality (GDS) | Assessment 4 | Done | Critical | 3 | 2026-10-10 | algorithms,gds
PRT-32 | Degree Centrality (GDS) | Assessment 4 | Done | High | 2 | 2026-10-11 | algorithms,gds
PRT-33 | Betweenness Centrality (GDS) | Assessment 4 | Done | High | 2 | 2026-10-12 | algorithms,gds
PRT-37 | Write Centrality section of report | Assessment 4 | Done | High | 3 | 2026-10-13 | documentation
PRT-41 | Integrate final report + embed figures | Assessment 4 | Done | Critical | 4 | 2026-10-15 | documentation
PRT-43 | Final QC and submit Assessment 4 | Assessment 4 | In Progress | Critical | 2 | 2026-10-16 | submission

## Dilliram's Board
Dilliram Dhakal – Personal Task Board
Tasks: 8 ¦ Done: 8 ¦ Story Points: 22/22 ¦ Completion: 100%
Key | Summary | Assessment | Status | Priority | Story Points | Due Date | Labels
PRT-3 | Research NT retail supply-chain constraints | Assessment 1 | Done | Medium | 2 | 2026-08-04 | research
PRT-9 | Draw UML class diagram | Assessment 2 | Done | High | 3 | 2026-08-20 | modelling
PRT-14 | Create Assessment 2 presentation slides | Assessment 2 | Done | High | 4 | 2026-09-08 | presentation
PRT-18 | Revise EER / normalisation / SQL topics | Assessment 3 | Done | High | 3 | 2026-09-20 | study
PRT-22 | Sit Individual Middle Semester Test | Assessment 3 | Done | Critical | 2 | 2026-09-26 | exam
PRT-26 | Create Bloom / graph model visualisation | Assessment 4 | Done | High | 3 | 2026-10-03 | modelling,visualisation
PRT-39 | Write Modelling + Implementation sections | Assessment 4 | Done | High | 3 | 2026-10-12 | documentation
PRT-40 | Write Discussions, Limitations, Conclusion | Assessment 4 | Done | Medium | 2 | 2026-10-14 | documentation

## Roshan's Board
Roshan Kumar Shrestha – Personal Task Board
Tasks: 9 ¦ Done: 9 ¦ Story Points: 30/30 ¦ Completion: 100%
Key | Summary | Assessment | Status | Priority | Story Points | Due Date | Labels
PRT-4 | Stakeholder analysis | Assessment 1 | Done | Medium | 2 | 2026-08-04 | planning
PRT-10 | Normalise schema to 3NF | Assessment 2 | Done | High | 4 | 2026-08-22 | modelling
PRT-11 | Implement SQLite DB + sample data | Assessment 2 | Done | Critical | 5 | 2026-08-28 | implementation
PRT-19 | Revise EER / normalisation / SQL topics | Assessment 3 | Done | High | 3 | 2026-09-20 | study
PRT-23 | Sit Individual Middle Semester Test | Assessment 3 | Done | Critical | 2 | 2026-09-26 | exam
PRT-27 | Write Cypher import scripts (constraints + data) | Assessment 4 | Done | Critical | 5 | 2026-10-05 | implementation,cypher
PRT-28 | Prepare CSV sample data files | Assessment 4 | Done | High | 3 | 2026-10-04 | data
PRT-29 | Write 4 Cypher query use cases | Assessment 4 | Done | High | 4 | 2026-10-08 | queries,cypher
PRT-30 | Run & screenshot Cypher use cases | Assessment 4 | Done | Medium | 2 | 2026-10-10 | evidence

## Dipesh's Board
Dipesh Sedhai – Personal Task Board
Tasks: 10 ¦ Done: 10 ¦ Story Points: 27/27 ¦ Completion: 100%
Key | Summary | Assessment | Status | Priority | Story Points | Due Date | Labels
PRT-5 | Risk register and timeline | Assessment 1 | Done | Medium | 2 | 2026-08-05 | planning
PRT-6 | Compile Group Project Plan document | Assessment 1 | Done | High | 4 | 2026-08-06 | documentation
PRT-12 | Write 4 SQL use cases | Assessment 2 | Done | High | 4 | 2026-08-30 | queries
PRT-20 | Revise EER / normalisation / SQL topics | Assessment 3 | Done | High | 3 | 2026-09-20 | study
PRT-24 | Sit Individual Middle Semester Test | Assessment 3 | Done | Critical | 2 | 2026-09-26 | exam
PRT-34 | Jaccard Node Similarity (GDS) | Assessment 4 | Done | Critical | 3 | 2026-10-11 | algorithms,gds
PRT-35 | Cosine Node Similarity (GDS) | Assessment 4 | Done | High | 2 | 2026-10-12 | algorithms,gds
PRT-36 | Screenshot all GDS results | Assessment 4 | Done | Medium | 2 | 2026-10-13 | evidence
PRT-38 | Write Similarity section of report | Assessment 4 | Done | High | 3 | 2026-10-13 | documentation
PRT-42 | Package repository (scripts + CSVs) | Assessment 4 | Done | High | 2 | 2026-10-15 | submission

## Sprint 4 Board (A4)
Sprint 4 – Assessment 4 Group Project Report (due 16 Oct 2026)
To Do | In Progress | In Review | Done | Blocked
| PRT-43 Final QC and submit Assessment 4 @Nitesh ¦ Critical ¦ 2sp Due: 2026-10-16 |  | PRT-25 Translate EER → Neo4j property graph model @Nitesh ¦ Critical ¦ 5sp Due: 2026-10-02
PRT-26 Create Bloom / graph model visualisation @Dilliram ¦ High ¦ 3sp Due: 2026-10-03
PRT-27 Write Cypher import scripts (constraints + @Roshan ¦ Critical ¦ 5sp Due: 2026-10-05
PRT-28 Prepare CSV sample data files @Roshan ¦ High ¦ 3sp Due: 2026-10-04
PRT-29 Write 4 Cypher query use cases @Roshan ¦ High ¦ 4sp Due: 2026-10-08
PRT-30 Run & screenshot Cypher use cases @Roshan ¦ Medium ¦ 2sp Due: 2026-10-10
PRT-31 PageRank centrality (GDS) @Nitesh ¦ Critical ¦ 3sp Due: 2026-10-10
PRT-32 Degree Centrality (GDS) @Nitesh ¦ High ¦ 2sp Due: 2026-10-11
PRT-33 Betweenness Centrality (GDS) @Nitesh ¦ High ¦ 2sp Due: 2026-10-12
PRT-34 Jaccard Node Similarity (GDS) @Dipesh ¦ Critical ¦ 3sp Due: 2026-10-11
PRT-35 Cosine Node Similarity (GDS) @Dipesh ¦ High ¦ 2sp Due: 2026-10-12
PRT-36 Screenshot all GDS results @Dipesh ¦ Medium ¦ 2sp Due: 2026-10-13
PRT-37 Write Centrality section of report @Nitesh ¦ High ¦ 3sp Due: 2026-10-13
PRT-38 Write Similarity section of report @Dipesh ¦ High ¦ 3sp Due: 2026-10-13
PRT-39 Write Modelling + Implementation sections @Dilliram ¦ High ¦ 3sp Due: 2026-10-12
PRT-40 Write Discussions, Limitations, Conclusion @Dilliram ¦ Medium ¦ 2sp Due: 2026-10-14
PRT-41 Integrate final report + embed figures @Nitesh ¦ Critical ¦ 4sp Due: 2026-10-15
PRT-42 Package repository (scripts + CSVs) @Dipesh ¦ High ¦ 2sp Due: 2026-10-15